## Purpose-Instructions
Getting Started in 340B Checklist
Purpose:
The purpose of this tool is to outline compliance and operational considerations for new 340B covered entities. Although all covered entities are likely to have differences in how they set up their programs, the areas covered in this tool will help sites understand the primary areas to consider.
This tool will:
• Focus on compliance, education and training, and purchasing insights elements critical for sites to consider during implementation of the 340B Program. • Reference helpful materials and resources available from the PVP in understanding and implementing the 340B Program. • Serve as a project management tool during implementation (optional). Note: This tool focuses on the steps for a covered entity to get started in the 340B Program; it does not address the steps needed to implement contract pharmacy. Additional steps may be required for contract pharmacy implementation.
Instructions:
• This tool is a template that your sites can add to/remove from based on which areas align to the way your program will be developed; customize it to best fit your needs based on the operations at your individual site. • Use the filters in columns E through I to organize the chart for desired time period of implementation (e.g., Prior to Going Live or Within First 3 Months).These are general timeframes; sites should customize timelines for tasks based on individual needs. • Use the headers in column A to help determine which person on your team may be responsible for those tasks based on the area of focus; another option could be to separate each of these task areas into different tabs of this document to allow easier visualization if different staff members will be responsible for each area. • Once the proper timeframe and tasks are identified, review each task and follow the instruction in the "How To" section; follow the links in column D to find more detailed instructions/education for each of these areas. • Certain tasks will reference 340B tools on the PVP website. Click the link to access the tools page, then expand the covered entity type and select the specified tool. • Tasks will also have links to HRSA, 340B PVP website pages, and videos to assist with the process. • Some tasks also have additional information available in cell comments that further elaborate on considerations related to that area. • (Optional) Use the final three columns as a Project Management Tool.
Project Management Tool (Optional):
• Use the final three columns as a record for the project implementation progress. • Review each task and assign it to a team member in the "Assign To" column. • Determine a timeline and document the due date in the "Complete By" column. • Document progress in the "Project Status" column.
This tool is written to align with Health Resources and Services Administration (HRSA) policy, and is provided only as an example for the purpose of encouraging 340B Program integrity. This information has not been endorsed by HRSA and is not dispositive in determining compliance with or participatory status in the 340B Drug Pricing Program. 340B stakeholders are ultimately responsible for 340B Program compliance and compliance with all other applicable laws and regulations. Apexus encourages all stakeholders to include legal counsel as part of their program integrity efforts.
© 2026 Apexus. Permission is granted to use, copy, and distribute this work solely for 340B covered entities and Medicaid agencies. Updated 09/15/2026
Task Category Legend
Compliance Related - CR
Education and Training - ET
Purchasing Insights - PI

## Covered Entity Checklist
Getting Started in 340B Checklist
Project Management Tool
Category | Task | How To/Resource | Links | Prior to Registration | Prior to Going Live | Within First 3 Months | Within First Year | Ongoing | Assigned To | Complete By | Project Status
Compliance Related
CR-1 | Determine site eligibility in anticipation of registration. | Confirm that the covered entity meets the applicable 340B eligibility requirements by checking the OPAIS Registration Guide. Coordinate with personnel responsible for maintaining documentation that supports the entity's eligibility. Identify locations and clinics that may qualify for 340B registration, gather supporting documentation, map eligible locations when appropriate, and identify the National Provider Identifiers (NPIs) used for billing at locations that will dispense or administer 340B-purchased medications. For health centers, coordinate with personnel responsible for maintaining the Electronic Handbooks (EHBs) and Section 330 grant information (if applicable). For hospital entities, coordinate with personnel responsible for maintaining the Medicare cost report. Identify clinics with reimbursable costs and charges, and, when applicable, map electronic medication administration record (eMAR) locations to the trial balance and the Medicare cost report. For specialized grantees, coordinate with personnel responsible for maintaining the applicable grant documentation. Helpful Hint: In addition to registration of sites, consider ship-to addresses that may need to be added to those sites. A ship-to address is typically used for any entity-owned pharmacies that have their own ordering accounts or addresses. They may also be needed if product is shipped to other sites where the product still belongs to the covered entity, such as a repackager or a lab. |  | X
CR-2 | Assemble expertise needed to make implementation decisions. | The 340B Program affects multiple departments across an organization. Engaging key stakeholders early supports informed implementation decisions. Common participants include: Pharmacy: Typically leads implementation because it is most directly affected. Reimbursement: Supports Medicare cost report (MCR) interpretation, National Provider Identifier (NPI) identification, and reimbursement decisions. Billing: Assesses Medicaid and Medicare billing requirements. Information Technology (IT): Supports data integration and split-billing or third-party administrator (TPA) software. Legal: Supports policy development and program decisions. Compliance: Develops auditing processes and supports responses to noncompliance. Helpful Hint: If your site does not have these expertises internally, evaluate the need for external resources (legal, consultants, auditors) using the 340B Tool: Independant Audit Request for Proposal Checklist |  | X
CR-3 | Identify all areas within the covered entity that will be using 340B and create a map of all areas. | Creating a map can help new programs understand operational decisions to be made, build appropriate data elements, and communicate effectively with the project team. |  | X
CR-4 | Determine which inventory model(s) will be used at your site(s). | Determine whether each participating setting will use replenishment or neutral inventory, physical inventory, or a hybrid model. Document differences by setting and operational need. Consider the effect of the selected model on purchasing, data feeds, split-billing software, and third-party administrator requirements. Grantee-style entities may commonly use physical inventory in clinics or retail pharmacies. Contract pharmacy arrangements often require replenishment inventory and a TPA. |  | X
CR-5 | Assess need for split-billing or third-party administrator (TPA) software. | Most hospitals use split-billing software for their mixed-use settings and a TPA for their retail pharmacy locations. Evaluate your inventory model, care settings, and available data to determine whether split-billing software, TPA software, or another auditable accumulation and replenishment process is needed. Identify the data required to support compliant replenishment and purchasing. Begin this assessment early, as software implementation may take 6–12 months. Helpful Hint: A helpful approach may be to map out the supply chain workflow and understand the data elements involved in the process. This may include data elements from the eMAR, ADT, billing systems, wholesaler, and inventory management systems. |  | X
CR-6 | Select and implement split-billing or TPA software. | For replenishment inventory models, determine whether split-billing software, TPA software, or another auditable accumulation and replenishment process is needed. Choose the software that best meets your operational and compliance needs. Configure and test the system to ensure accurate accumulation, replenishment, and purchasing based on eligible utilization. Helpful Hint: Ensure that you are working closely with your software and your wholesaler in the setup of your accounts. It is critical for information from the wholesaler accounts to feed into the software to ensure proper functionality, so it is helpful to have a full listing of wholesaler accounts during software setup. Both the software vendor and your wholesaler should be familiar with the process and able to walk you through those steps. |  | X
CR-7 | Develop entity-specific policies and procedures. | Before going live, document how the entity will meet the core operational and compliance elements applicable to its 340B program. Policies and procedures should align with the selected inventory model, registration structure, Medicaid approach, purchasing processes, software configuration, audit methods, records, training, and noncompliance response. Ensure that actual operations match the approved procedures. |  | X
CR-8 | Determine whether your sites will carve in or carve out Medicaid. | At registration, covered entities will need to articulate which states and which NPIs are using 340B-purchased medications when billing Medicaid fee-for-service (FFS) (known as "carving in" Medicaid). Coordinate with reimbursement and billing personnel to identify all relevant clinic, institutional, and pharmacy NPIs. Consider the effect of the decision on the split-billing or TPA configuration, patient billing systems, pharmacy systems, and wholesaler accounts. |  | X
CR-9 | Register eligible sites in OPAIS. | OPAIS registration is open during the first 15 days of each calendar quarter for an effective date of the first day of the following quarter. Use the information gathered on lines CR-1 and CR-8 to register each associated site, including appropriate NPIs (if carving in) and shipping addresses. |  | X
CR-10 | Ensure that covered entity information is accurate on OPAIS. | Verify that all participating sites are accurately listed, including child or associated sites where applicable. Confirm Medicaid carve-in or carve-out information, contacts, addresses, and other registration information. Establish a process to update OPAIS when organizational or operational information changes. |  |  | X
CR-11 | Contact wholesaler to set up 340B accounts. | Begin account setup early because wholesalers may require 4 to 8 weeks to establish new accounts. Establish the appropriate account types for each distributor or supplier, not only the primary wholesaler. Your wholesaler will likely require your registration to first be approved by HRSA before it can set up accounts. Entities without an existing distributor relationship may need to identify an authorized distributor. If you do not already have a wholesaler account, you can access the list of PVP authorized distributors (and their contacts) at the link provided. Hospital entities should determine whether WAC accounts are required in addition to 340B accounts. | PVP Distributors in Network |  | X
CR-12 | Identify state-specific requirements for Medicaid FFS and MCO and ensure that your systems are set up to comply. | For each state where Medicaid claims are billed and 340B-purchased products may be used, identify billing requirements for Medicaid fee-for-service and managed care. Confirm accurate Medicaid FFS information in the Medicaid Exclusion File and implement any state-required claim modifiers. Configure and test billing systems before go-live and retain documentation of state requirements. The reference link provided gives a starting point for researching state-specific 340B billing requirements. |  |  | X
CR-13 | Ensure adequate resources/roles to support the program. | Identify the ongoing responsibilities required to operate and monitor your 340B program. Assign accountable owners and determine whether existing staffing, expertise, and technology are sufficient. |  |  | X
CR-14 | Create a 340B oversight council. | Ensure program integrity through oversight and support at the entity level by developing an oversight team composed of leaders from areas directly involved in 340B program operations and planning: C-suite, reimbursement, IT, billing, contracting/purchasing, compliance/legal, pharmacy, and patient assistance/advocacy. This group reviews core compliance monitoring, ensures strategic alignment, and makes high-level decisions for program implementation. |  |  |  | X
CR-15 | Conduct frequent audits to identify and address issues affecting 340B program operations. | Perform regular software, operational, and staff audits to identify issues such as missing or incorrect data feeds, system errors, operational barriers, staff knowledge gaps, or incomplete auditable records. Review unexpected data trends or system exceptions, observe key staff workflows (e.g., purchasing and billing), and conduct dispensation audits as needed (see Prevention of Diversion Tool, CR-16) to verify that auditable records are complete, accurate, and accessible. Address identified issues promptly and document corrective actions. |  |  |  | X
CR-16 | Develop regular audit plans. | Ongoing program audits are critical for maintaining the integrity of the program. The PVP has developed a series of self-audit tools to help guide this process, but each site may develop its own audits and frequency based on its unique operations. Most sites complete self-audits at least monthly. |  |  |  | X
CR-17 | Prepare for a HRSA audit. | Develop a plan for how you will respond if HRSA were to select you for an audit. This includes knowing whom to involve within your organization, understanding how to quickly pull together the the information requested by HRSA, and having a communication plan within your leadership team to provide appropriate updates in a timely manner. Keeping all the necessary records in a single location such as a shared drive or cloud-based platform can help make the process of responding to HRSA more smooth. |  |  |  |  | X
CR-18 | Establish a process for responding to noncompliance. | It is important that once you do identify an issue of noncompliance, your site has a process to resolve these issues. This typically involves repayment to the manufacturer and potentially reporting to HRSA. New covered entities will need to define a materiality threshold for reporting to HRSA. |  |  |  | X
CR-19 | Understand expectations for annual recertification. | HRSA expects all covered entities to recertify annually. Specific recertification window dates vary from year to year, but each year HRSA will send a notification to both the authorizing official and primary contact with details. |  |  |  |  | X
CR-20 | Review PVP tools for any other areas to develop. | A variety of other 340B tools are available that address specific situations that may apply to your entity (e.g., CSOS ordering, consignment compliance). | [5 empty] | X
CR-21 | Use HRSA FAQs to find guidance on many compliance elements. | FAQs are written by HRSA to address a variety of common questions. These FAQs can be searched or scanned by topic. Many FAQs are available on the HRSA website, and additional FAQs are available by reaching out to Apexus Answers. | [5 empty] | X
CR-22 | Use Apexus Answers to help with 340B or PVP questions. | Apexus Answers is a free service that offers technical assistance for many 340B questions. If you can't find your answers anywhere else, reach out to Apexus Answers to see if it has additional resources to direct you to. | [5 empty] | X
Education and Training
ET-1 | Learn the basics of the 340B Program. | 340B University OnDemand is series of online educational modules that you can access at any time. Completion of OnDemand may help key members of the go-live team understand 340B Program requirements when developing the project plan. |  | X
ET-2 | Develop a training plan for staff. | Developing a training plan for staff can help ensure that your team is ready to go live. You can review the list of OnDemand modules and assign some or all of these modules to staff, depending on their role. Roles to consider for education may include puchasing, billing, auditing, operations, IT, contracting, and leadership. Those who may be only minimally involved in the program may not want to sign up for OnDemand, so a link is provided for just the Basics module for easy access. |  |  | X
ET-3 | Create an onboarding/training plan for new staff. | It is important to ensure that even after going live, all new staff who will be working with the 340B Program receive proper training. The education resources found on lines ET-1 and ET-2 can be combined with internal references and tools to familiarize staff with their roles in maintaining program integrity. |  |  |  | X
ET-4 | Subscribe to receive FAQ and 340B tool updates. | The PVP offers the ability to subscribe to RSS feeds to alert you to any changes to our 340B tools or HRSA FAQ pages. If you are unfamiliar with how to subscribe to an RSS feed, instructions are provided in the link to the right. |  |  |  |  | X
ET-5 | Create annual staff competency training for 340B. | It is a best practice to ensure that staff maintain ongoing training in the 340B Program. Many sites build their own competency trainings or use 340B University resources to complete annual refreshers for staff. Helpful Hint: Annual 340B training can be tracked in 340B University OnDemand. When staff re-watch a specific module, the module completion date is updated with a corresponding time stamp. Certificates of completion are issued after you complete the full OnDemand Core Curriculum and each subsequent Annual Refresher. An important element in creating your staff training will be incorporating your own site's operational implementation of the subjects covered in the resources provided. Many sites find it best to add an additional training element (via module development, P&P review, or other means) to incorporate expectations for staff at their site. |  |  |  |  | X
Purchasing Insights
PI-1 | Enroll in the PVP to access 340B Program contract savings. | As the 340B Prime Vendor, Apexus negotiates sub-340B pricing and other discounts with many manufacturers. This program is available to any covered entity at no cost to the entity. However, sites must take the additional step of enrolling in the PVP to see these contracts loaded on their accounts. |  |  | X
PI-2 | Verify with your wholesaler(s) that PVP contracts are loaded. | Reach out to your wholesaler representative(s) for a listing of all 340B and WAC accounts. Verify with the wholesaler that PVP contracts have been loaded to all accounts. A further verification step may be to run a validation to ensure that pricing is loaded consistently across all accounts of the same account type (e.g., all 340B accounts). The 340B PVP catalog can be a good resource to identify contract pricing and other price types that you should expect to see on your accounts. |  |  | X
PI-3 | Get access to the PVP participant site and delegate who will need access to the catalog. | The PVP participant website has a variety of resources. Getting access for your team early can ensure that they are able to access resources mentioned in this checklist in a timely manner. The catalog is the most commonly used resource on this page and is helpful for verifying pricing information. |  |  | X
PI-4 | Update site profile on the PVP website. | Once you have a PVP participant site sign-on, you are able to log into 340Bpvp.com; click on the site in the upper right corner, select "my profile," and select a specific site. Here you can review your site's information in the PVP system, make changes to the primary distributor, and add/change contacts for your site. Contacts added will automatically receive Prime Vendor Updates and will receive an email asking them to create a sign-on for the PVP participant site. |  |  |  | X
PI-5 | Sign up for regular contract announcements through Prime Vendor Updates. | The PVP sends monthly Prime Vendor Updates to all participants. To sign up, click "Sign up for PVP Emails" in the upper right corner of the 340Bpvp.com website. |  |  |  | X
PI-6 | Use resources on the secure site to support purchasing decisions. | A variety of tools are available on the PVP website. To access these tools, staff will need to have a login for the PVP participant site (see line PI-3). These resources include pricing, contract, and ordering information. | [5 empty] | X
PI-7 | Audit accounts to ensure contract load accuracy and pricing accuracy. | The PVP site also contains a downloadable catalog that sites can use to compare product pricing to their wholesaler catalog. This can be especially important at account setup. One important thing to note is that small discrepancies may exist between the two sources of information because of factors such as wholesaler cost-minus and distribution fees. | [5 empty] | X
PI-8 | Regularly review purchase reports to identify ordering anomalies. | The purchasing analytics section allows covered entities to review reports of their site's purchasing to identify trends, anomalies, and savings opportunities. | [5 empty] | X
OPAIS Registration Guide
HRSA Audit Overview
340B Tool: Sample HRSA 340B Audit Data Request List (DRL) for Covered Entities
OPAIS Registration Guide
340B Tools: Visit the Tools Resource Center. Go to "All Tools +" and click to expand the menu. Scroll down to the Internal Self Audit section for Eligibility tools by covered entity type.
340B Tool: Understanding the Medicare Cost Report
OnDemand Module: 340B Drug Delivery Models
340B Tools: Visit the Tools Resource Center. Go to "All Tools +" and click to expand the menu. Scroll down to the Policy and Procedures Manuals section. Select your covered entity type.
340B Tools: Visit the Tools Resoure Center. Go to "All Tools +" and click to expand the menu. Scroll down to the Internal Self Audit section for Eligibilty tools by covered entity type.
340B Tool: Non-GPO/WAC and 340B Contract Load Options
340B Tool: 340B Coordinator Job Description Template
340B Tool: 340B Analyst Job Description Template
340B Tool: 340B FTE Request Template
Validate on OPAIS
State Medicaid Profiles
340B Tool: 340B Oversight Best Practices Dashboard
340B Tool: Calculating 340B Net Financial Impact and Use of Savings
340B Tool: C-Suite Guide to the 340B Program
340B Tools: Visit the Tools Resource Center. Go to "All Tools +" and click to expand the menu. Scroll down to the Internal Self-Audit section for tools by covered entity type.
340B Tool: Establishing Material Breach Threshold
340B Tool: Self-Disclosure to HRSA and Manufacturer Template
HRSA FAQs
Apexus Answers
Apexus Answers
340B University OnDemand
Supplemental Course: 340B for the C-Suite
340B University OnDemand > Core Curriculum
PVP RSS Feed
Enroll in PVP
340B PVP Catalog
340B Tool: Non-GPO/WAC and 340B Contract Load Options (for GPO-Prohibition Hospitals)
Request Access
PVP Catalog
340B Tool: Medicaid Exclusion File (MEF) Checklist
340B Tool: Medicaid Exclusion File (MEF) Checklist
OnDemand Module: 340B & Medicaid; HRSA's Medicaid Exclusion File
340B Tool: 340B Universe Mapping (Excel) Template
Purchasing Decision Resources
My Purchasing Analytics
PVP Distributors in Network
340B Tool: Independent Audit Request for Proposal Checklist
Help Center
340B University OnDemand > Core Curriculum
340B University OnDemand > Annual Refresher